## Sheet1
www.goodoldmanoj.com
Sprint 1: Burn down chart
Project | Story | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
ProjectRothar | Repo | Create shared Repo | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ProjectRothar | Data | Write Function | 2 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ProjectRothar | Data | Create Table | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
ProjectRothar | Data | Loop to append requests for entire week | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
ProjectRothar | Server Setup | Run Scrapper | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0
Ideal - Remaining efforts in uninterrupted working hours |  |  | 9 | 8.1 | 7.2 | 6.3 | 5.4 | 4.5 | 3.6 | 2.7 | 1.8 | 0.9 | -1.5543e-15
Actual - Remaining efforts in uninterrupted working hours |  |  | 9 | 9 | 8 | 8 | 5 | 3 | 3 | 3 | 3 | 1 | 0