## Sheet1
www.goodoldmanoj.com
Sprint 3: Burn down chart
Project | Story | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
ProjectRothar | Testing | JS error handling | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ProjectRothar | Flask App | Handle DB requests | 3 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ProjectRothar | UI | Style Station Info Window | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ProjectRothar | UI | Style Google Map | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ProjectRothar | Historical Chart | Create Chart | 3 | 3 | 3 | 3 | 4 | 3 | 2 | 0 | 0 | 0 | 0
ProjectRothar | Geolocation and Routing | Get location of user | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
ProjectRothar | Geolocation and Routing | Find nearest station | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 0 | 0 | 0
ProjectRothar | Geolocation and Routing | Display route | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
ProjectRothar | Locate nearest station to planned Dest. | Location of user | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
ProjectRothar | Locate nearest station to planned Dest. | Find nearest station | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
ProjectRothar | Locate nearest station to planned Dest. | Display route | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
ProjectRothar | Project Package | venv to req.txt | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
ProjectRothar | Project Package | App to package | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Ideal - Remaining efforts in uninterrupted working hours |  |  | 25 | 22.5 | 20 | 17.5 | 15 | 12.5 | 10 | 7.5 | 5 | 2.5 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  | 25 | 24 | 21 | 19 | 18 | 17 | 16 | 15 | 8 | 5 | 4